## Cover
REAL RAILS · FUNCTIONAL UAT DOCUMENT
Real-Time Payments Map · PoC #05 · Post-VAR Approval · April 2026
PROJECT |  | PoC #05 — Real-Time Payments Map
ARTIFACT |  | real-rails-connectivity-final.jsx + main.py (FastAPI)
VAR STATUS |  | APPROVED — 22 PASS · 1 NOTE · 0 FAIL
DATA SOURCES |  | FedNow (Federal Reserve) · EPC (SEPA) · World Bank · BIS (NEXUS)
UAT SCOPE |  | Handshake · Filter Logic · Intelligence Value · API & Metrics
TOTAL TCs |  | 30 test cases across 4 sections
PASS GATE |  | All HIGH priority TCs must pass · 0 FAIL tolerance
DATE |  | April 2026
SECTION OVERVIEW
SECTION | TCs | DIMENSION TESTED | PRIORITY | SHEET
1 · Handshake | 8 TCs | Node click → sidebar metadata population | HIGH | UAT Checklist
2 · Filter Logic | 10 TCs | Cluster / edge type / TX path filters | HIGH | UAT Checklist
3 · Intelligence | 7 TCs | 'Who Controls the Rail' + data accuracy | MEDIUM | UAT Checklist
4 · API & Metrics | 5 TCs | useEffect fetch · fallback · counts | HIGH | UAT Checklist
PASS GATE · All HIGH priority TCs must pass · 0 FAIL tolerance on Handshake + Corridor + API tests · Sign-off: UX Architect + Product Owner

## UAT Checklist
REAL RAILS · FUNCTIONAL UAT CHECKLIST · PoC #05 · Real-Time Payments Map · Fill column F with PASS / FAIL / BLOCKED
TC ID | SECTION | TEST CASE | EXPECTED RESULT | ACTUAL RESULT (Tester Fills) | PASS / FAIL | PRIORITY | SOURCE / NOTES
SECTION 1 — HANDSHAKE: Does clicking a node in the 70% area populate the 30% sidebar with correct metadata? (TC-001–008)
TC-001 | 1 · Handshake | UPI Node Click → Sidebar Populates NODE DETAIL | Click UPI circle in 70% graph. NODE DETAIL tab activates automatically. Sidebar shows: label='UPI', cluster='RTP RAILS', sub='India · NPCI · 400M/d'. Edge list appears with ▶/◀ direction indicators. | [ Enter actual result ] | PENDING | HIGH | NPCI/RBI · setSideTab('node') fires on click
TC-002 | 1 · Handshake | SWIFT Node → Correct Shape + Correspondent Metadata | Click SWIFT diamond node. Sidebar: label='SWIFT', cluster='CORRESPONDENT', sub='Global Messaging'. Edge list shows MT103 outbound. Shape is diamond (correspondent shape-code). | [ Enter actual result ] | PENDING | HIGH | BIS/SWIFT · diamond = correspondent cluster
TC-003 | 1 · Handshake | Node Deselect → Sidebar Resets to Empty State | Click any node to select. Click same node again. selectedNode returns to null. Sidebar NODE DETAIL shows: 'Click a node on the graph'. | [ Enter actual result ] | PENDING | MEDIUM | React state toggle · onSelectNode(id===selectedNode?.id ? null : n)
TC-004 | 1 · Handshake | Edge Hover → Tooltip: Label + Hop Number + Type | Hover any edge. SVG tooltip appears at edge midpoint showing: edge label (e.g. 'NEXUS (pilot)'), hop number ('HOP 1'), type uppercase ('CORRIDOR'). Tooltip border matches edge color. | [ Enter actual result ] | PENDING | HIGH | EDGES array · tooltip rendered at bezier midpoint
TC-005 | 1 · Handshake | NEXUS Edge Hover → Pink Tooltip Confirming Corridor Type | Hover the pink edge between UPI and PayNow nodes. Tooltip shows: label='NEXUS (pilot)', HOP=1, TYPE=CORRIDOR. Border is pink (#F472B6). Confirms FIX-01 edge renders correctly. | [ Enter actual result ] | PENDING | HIGH | BIS NEXUS pilot · FIX-01 + FIX-02 validation
TC-006 | 1 · Handshake | FinTech App Node → 'Licensed Participant' Sub-label | Click FinTech App hex node. Sub-label='Licensed Participant'. cluster='user'. Color=amber. Confirms intelligence claim: FinTechs never own a direct rail seat. | [ Enter actual result ] | PENDING | HIGH | BIS/FCA regulatory framework · core intelligence claim
TC-007 | 1 · Handshake | Sending Bank → ▶ Outbound / ◀ Inbound Direction Indicators | Click 'Sending Bank' node. Connected edges list shows: ▶ (cyan) on outbound edges, ◀ (emerald) on inbound edges. All edges labeled (e.g. 'Pix Route', 'MT103', 'Instant Pay'). | [ Enter actual result ] | PENDING | HIGH | EDGES array · dir = e.from===selectedNode.id ? 'out' : 'in'
TC-008 | 1 · Handshake | Sidebar Tab Auto-Switches on Node Click | Navigate to INSIGHTS tab in sidebar. Click any node on graph. Sidebar immediately switches to NODE DETAIL tab. setSideTab('node') fires on handleSelectNode call. | [ Enter actual result ] | PENDING | MEDIUM | React state · if (node) setSideTab('node')
SECTION 2 — FILTER LOGIC: Do the filters accurately update the visualization? (TC-009–018)
TC-009 | 2 · Filter Logic | Supply Chain Cluster Button Visible + Functional | All 7 cluster buttons visible (flex-wrap allows second row). Click 'Supply Chain'. Only supplychain cluster nodes at full opacity: ERP, SCF Platform, Supplier, Buyer Corp. All others dim. | [ Enter actual result ] | PENDING | HIGH | FIX-03 flex-wrap validation · 4 supplychain nodes
TC-010 | 2 · Filter Logic | RTP Rails Cluster Filter Isolates Rail Nodes | Click 'RTP Rails' button. Only RTP cluster nodes at full opacity. All other clusters (user, card, OB, correspondent, supplychain) dim to ~20% opacity. | [ Enter actual result ] | PENDING | HIGH | CLUSTER_META · clusterFilter='rtp'
TC-011 | 2 · Filter Logic | ALL Button Resets Cluster Filter | Activate any cluster filter. Click ALL. All nodes restore to full opacity. ALL button shows cyan active state (cyan background + border + glow). | [ Enter actual result ] | PENDING | HIGH | setClusterFilter(null) · active style: C.cyan+20 bg
TC-012 | 2 · Filter Logic | Corridor Edge Type Filter — Exactly 4 Pink Edges | Click 'corridor' in header edge type filter bar. Exactly 4 pink (#F472B6) edges visible: NEXUS (UPI→PayNow), PayNow→FPS, EPC↔Pay.UK (SEPA→FPS), SWIFT GPI (FedNow→SEPA). All other edges hidden. | [ Enter actual result ] | PENDING | HIGH | FIX-01 + FIX-02 · 4 corridor edges · type='corridor'
TC-013 | 2 · Filter Logic | Payment Edge Type Filter — Cyan Edges Only | Click 'payment' in header filter. Only cyan payment-type edges visible. Data, auth, settlement, corridor edges all dim/hide. edgeTypeFilter='payment'. | [ Enter actual result ] | PENDING | HIGH | EDGES · edgeTypeFilter='payment' · cyan color
TC-014 | 2 · Filter Logic | Domestic RTP TX Path — 7-Hop Cyan Sequence | Click 'Domestic RTP (UPI)' in TX PATHS tab. 7 nodes pulse with cyan rings: consumer→fintech→send_bank→send_cb→rtp_upi→recv_bank→business. Hop tracer animates at 900ms. Counter 1/7 → 7/7. | [ Enter actual result ] | PENDING | HIGH | NPCI/RBI UPI spec · 7 hop exact sequence
TC-015 | 2 · Filter Logic | All 6 TX Paths Accessible in Sidebar (Scroll to Confirm) | Scroll TX PATHS tab. All 6 paths listed: Domestic RTP(7), Card Payment(8), Cross-Border SWIFT(8), Open Banking(5), Supply Chain(6), NEXUS Cross-Border(7). Each has color, hop count, description. | [ Enter actual result ] | PENDING | HIGH | FIX-04 NEXUS path · 6 paths total in TX_PATHS
TC-016 | 2 · Filter Logic | NEXUS TX Path — 7 Pink Hops Correct Sequence | Click 'NEXUS Cross-Border (UPI↔PayNow)'. 7 nodes pulse pink (#F472B6): consumer→send_bank→send_cb→rtp_upi→rtp_paynow→recv_bank→business. Counter 1/7 → 7/7. Settlement: <60 seconds. | [ Enter actual result ] | PENDING | HIGH | BIS NEXUS pilot · FIX-04 · 7 hop exact sequence
TC-017 | 2 · Filter Logic | Combined Cluster + Edge Type Filter Works Correctly | Select 'RTP Rails' cluster. Then select 'payment' edge type. Only payment edges where BOTH from and to nodes are in RTP cluster remain visible. Other combinations hidden. | [ Enter actual result ] | PENDING | HIGH | Filter composition · visibleNodeIds AND edgeTypeFilter
TC-018 | 2 · Filter Logic | TX Path Deactivation Toggle | Activate any TX path. Click same path button again. activePath returns to null. All nodes restore full opacity. Hop tracer footer disappears. | [ Enter actual result ] | PENDING | MEDIUM | setActivePath(prev=>prev?.id===path.id ? null : path)
SECTION 3 — INTELLIGENCE VALUE: Does the 'Who Controls the Rail' panel reflect the DataSource findings? (TC-019–025)
TC-019 | 3 · Intelligence | 'Who Controls the Rail' — 4 Rows Present and Accurate | INSIGHTS tab > WHO CONTROLS THE RAIL panel shows exactly 4 rows: RTP Rails=Central bank operated ¦ Card Networks=Private consortium (Visa/MC) ¦ Correspondent=Bilateral bank agreements ¦ Open Banking=Regulator mandated APIs. | [ Enter actual result ] | PENDING | HIGH | FedNow · EPC · BIS · core intelligence claim for allocators
TC-020 | 3 · Intelligence | SWIFT = Messaging Layer, NOT Settlement | Click SWIFT node. sub='Global Messaging', cluster='CORRESPONDENT'. INSIGHTS: Correspondent=Bilateral bank agreements. SWIFT sends payment instructions only — actual settlement via Nostro/Vostro accounts. | [ Enter actual result ] | PENDING | HIGH | BIS/SWIFT cooperative · critical cross-border distinction
TC-021 | 3 · Intelligence | FedNow = Central Bank Operated, NOT Private | Click FedNow node. sub='USA · Fed Reserve'. INSIGHTS: RTP Rails=Central bank operated. Correctly distinguishes FedNow from Visa/MC which are private consortia. | [ Enter actual result ] | PENDING | HIGH | Federal Reserve · July 2023 launch · iso20022=true
TC-022 | 3 · Intelligence | NEXUS Labeled as Pilot — Zero Hallucination Confirmed | Hover NEXUS corridor edge. Tooltip shows 'NEXUS (pilot)'. TX path description: 'BIS NEXUS pilot: instant cross-border India→Singapore in <60 seconds'. NOT labeled production. Source: BIS. | [ Enter actual result ] | PENDING | HIGH | BIS NEXUS 2024 · zero hallucination policy
TC-023 | 3 · Intelligence | INSIGHTS Edge Legend — All 5 Types with Corridor | INSIGHTS tab > EDGE TYPES section shows 5 rows: payment · data · auth · settlement · corridor. Corridor row: 'Cross-border interop link — NEXUS / TIPS / SWIFT GPI' in pink (#F472B6). | [ Enter actual result ] | PENDING | HIGH | FIX-08 INSIGHTS legend · 5 types documented
TC-024 | 3 · Intelligence | Footer Attribution — All 5 Sources Cited | Sidebar footer shows: 'Sources: FedNow · EPC · World Bank · ISO 20022 · BIS (NEXUS)'. All 5 sources present. BIS added in FIX-09. | [ Enter actual result ] | PENDING | HIGH | FIX-09 · data governance · 5 sources cited
TC-025 | 3 · Intelligence | 'Why This Matters' Panel — Money Velocity Narrative | INSIGHTS tab > WHY THIS MATTERS panel explains: instant rails reveal where friction lives, where settlement velocity is unlocked. References global GDP velocity-of-money research. | [ Enter actual result ] | PENDING | MEDIUM | World Bank GPSS · velocity of money narrative
SECTION 4 — API & METRICS: Backend connection, data accuracy, and graph metric counts (TC-026–030)
TC-026 | 4 · API & Metrics | Graph Metrics Cards — 28 / 44 / 6 / 8 | GRAPH METRICS section shows: 28 Entities · 44 Connections · 6 Clusters · 8 Max Hops. These are the post-fix correct values matching code: NODES.length=28, EDGES.length=44. | [ Enter actual result ] | PENDING | HIGH | Post-fix validation · 28 nodes, 44 edges confirmed
TC-027 | 4 · API & Metrics | API LIVE — Green Dot When Backend Running | Run: uvicorn main:app --reload --port 8000. Header shows green dot + 'API LIVE' text. apiStatus='live'. useEffect fetch resolved successfully. | [ Enter actual result ] | PENDING | HIGH | FastAPI · useEffect fetch · FIX-07 wiring
TC-028 | 4 · API & Metrics | API OFFLINE — Red Dot + Static Fallback Works | Stop FastAPI server. Reload frontend. Header shows red dot + 'API OFFLINE · STATIC'. Dashboard remains FULLY functional — all 28 nodes, 44 edges, 6 TX paths render from static data. | [ Enter actual result ] | PENDING | HIGH | Fallback resilience · catch(()=>setApiStatus('error'))
TC-029 | 4 · API & Metrics | GET /api/schemes/IN — UPI Data Accurate | GET localhost:8000/api/schemes/IN. Response: {code:'IN', scheme:'UPI', launch_year:2016, maturity:'Leader', iso20022:false, daily_volume_m:400, tx_limit_usd:2400}. iso20022=false confirms NPCI proprietary spec. | [ Enter actual result ] | PENDING | HIGH | NPCI/RBI · iso20022=false for UPI confirmed
TC-030 | 4 · API & Metrics | GET /api/schemes/XX — Zero Hallucination 404 | GET localhost:8000/api/schemes/XX. HTTP 404 response: {'error': 'Country not found or status unknown'}. No fabricated scheme data returned. | [ Enter actual result ] | PENDING | HIGH | Zero hallucination guardrail · main.py 404 handler
SIGN-OFF CRITERIA: All 25 HIGH priority TCs must PASS · Fill 'PASS' in column F after physical testing · Final deliverable = Screenshot + completed this checklist · Submit to Discussion #10

## Execution Tracker
UAT EXECUTION TRACKER — Real-Time Payments Map · PoC #05
SECTION | TCs | PASS | FAIL | PASS RATE
1 · Handshake | 8 | — | — | TBD
2 · Filter Logic | 10 | — | — | TBD
3 · Intelligence Value | 7 | — | — | TBD
4 · API & Metrics | 5 | — | — | TBD
TOTAL | 30 | — | — | —
PASS CRITERIA
MANDATORY |  | All 25 HIGH priority TCs must PASS before production approval
ZERO TOLERANCE |  | TC-005 (NEXUS edge), TC-012 (Corridor filter), TC-027/028 (API) — no failures accepted
FAIL TOLERANCE |  | Up to 2 MEDIUM priority failures acceptable with documented workaround
SIGN-OFF |  | UX Architect + Product Owner must co-sign UAT completion
FINAL DELIVERABLE |  | Screenshot (post-UAT) + this completed checklist → submit to Discussion #10